## Project Planner
Sprint 2 - Accuracy
Select a period to highlight at right. A legend describing the charting follows. | [5 empty] | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | Complete |  |  |  |  | Planned Start | [7 empty] | Planned Complete
| STAFF MEMBER(S) | PLAN START (Hours) | PLAN DURATION (Hours) | ACTUAL START (Hours) | ACTUAL DURATION (Hours) | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Gantt Chart | Dennis Vaccaro | 1 | 16 | 1 | 11 | 100% | bar: PERIODS 1; PERIODS 11; PERIODS 16
requirements table | Jack Staker | 1 | 7 | 1 | 2 | 100% | bar: PERIODS 1; PERIODS 3; PERIODS 7
Requirement signoff table | Jack Staker | 6 | 1 | 9 | 1 | 100% | bar: PERIODS 6; PERIODS 8 to PERIODS 9
algorithm | Chalen Bobish | 1 | 1 | 1 | 1 | 100% | bar: PERIODS 1 to PERIODS 2
flowchart | Chalen Bobish | 2 | 1 | 2 | 1 | 100% | bar: PERIODS 2 to PERIODS 3
block code | Dennis Vaccaro | 2 | 1 | 2 | 8 | 100% | bar: PERIODS 2; PERIODS 4; PERIODS 10
sensor data diagram | Dennis Vaccaro | 3 | 1 | 3 | 2 | 100% | bar: PERIODS 2 to PERIODS 4; PERIODS 10
test table | Dennis Vaccaro | 2 | 1 | 2 | 1 | 100% | bar: PERIODS 2 to PERIODS 4; PERIODS 10
staffing plan | Chalen Bobish | 1 | 10 | 1 | 10 | 100% | bar: PERIODS 1 to PERIODS 2
system design doc | Jack Staker | 1 | 20 | 1 | 16 | 100% | bar: PERIODS 1; PERIODS 11; PERIODS 16
robot video | Chalen Bobish | 3 | 7 | 3 | 7 | 100% | bar: PERIODS 3; PERIODS 10
github repository | Dennis Vaccaro | 1 | 17 | 1 | 12 | 100% | bar: PERIODS 1; PERIODS 11; PERIODS 17
Test Robot | All Group Members | 1 | 3 | 2 | 1 | 100% | bar: PERIODS 1; PERIODS 3; PERIODS 11
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%